- Pacific World Heritage Action Plan 2010-2015

- Vision for 2015

We share a dream that our Pacific Islands’ heritage is protected and enriched for future generations.

- Preamble

We the people of the Pacific Islands offer a unique contribution to the World Heritage community, through the enormous wealth of cultural diversity, as well as of the island and marine biodiversity of our region, much of which is endemic, and covers one third of the earth’s surface.

For us, indigeneity is inseparable from heritage. Our indigeneity has the following characteristics:

- Heritage in the Pacific defines our cultural identity and remains inseparable from oursocial, economic and environmental well-being, now and for future generations;

- Our heritage is holistic, embracing all life, both tangible and intangible, and isunderstood through our cultural traditions;

- There is an inseparable connection between the outstanding seascapes and landscapes in the Pacific Islands region, which are woven together by the rich cultural, historical and genealogical relationships of Pacific Island peoples;

- The region contains a series of spectacular and highly powerful spiritually-valued natural features and cultural places. These places are related to the origins of peoples, the land and sea, and other sacred stories;

- The Pacific is a region of distinct and diverse responses to oceanic environments;

- Protection of our heritage must be based on respect for and understanding and maintenance of the traditional cultural practices, indigenous knowledge and systems of land and sea tenure in the Pacific.

This extraordinary heritage, moreover, is often managed through traditional practices that reinforce the inseparable relationship between communities, cultures and environment that underpin sustainable development.

Noting our achievements since the creation of the Pacific World Heritage Action Plan 2004 – 2009, including:

- Twelve Pacific islands countries (out of fifteen) have ratified the Convention, including Cook Islands, Fiji, Niue, Palau, Papua New Guinea, Kiribati, Marshall Islands, Federated States of Micronesia, Samoa, Solomon Islands, Tonga and Vanuatu.

- Nine States Parties have submitted their Tentative Lists, including Fiji, Kiribati, Marshall Islands, Federated States of Micronesia, Palau, Papua New Guinea, Samoa, Tonga and Vanuatu.

- Three properties from Pacific Small Islands State Parties are now inscribed on the World Heritage List, i.e. Kuk Early Agricultural Site, PNG; Chief Roi Mata’s Domain, Vanuatu, in addition to East Rennell, Solomon Islands, which was inscribed in 1998.

- Four Properties from Pacific territories of non-Pacific State Parties are now inscribed on the World Heritage List, i.e. Lagoon of New Caledonia: Reef Diversity and Associated Ecosystem, France, in addition to Hawaiian Islands Volcanos, USA; Henderson Island, UK; Rapa Nui, Chile, which had been inscribed prior to 2004;

- A greatly increased awareness and understanding of the World Heritage Convention has been achieved;

- A regional network of heritage practitioners has been developed;

- A shared long-term vision on World Heritage for the region was established and communicated, through the so-called “Pacific Appeal”.

- Common Challenges to the Pacific region

We recognise that the Pacific region continues to be the most under-represented region on the World Heritage List. In redressing this imbalance in representation and endeavouring to continue to build on the aforementioned achievements, the Pacific Island States face major challenges. These include:

- Limited awareness of Pacific cultural and natural heritage outside the region;

- Lack of adequate representation of the unique and special heritage of the Pacific on the World Heritage List;

- Large geographic area, isolation and resource limitations that restrict access to information and assistance and the ability of Pacific people to contribute to global forums;

- The character and scope of the UNESCO and the World Heritage Convention administration for the Pacific region, which masks some of the specific important national and regional heritage issues;

- Some people are represented by States Parties outside the region (UK, France, USA, Chile) which can limit their ability to have sites inscribed on the World Heritage List;

- Limited financial and human resources, skills and capacities within communities and institutions to adequately manage the region’s cultural and natural heritage;

- A need for increased awareness within communities of the great value that World Heritage Convention contributes to the protection and vitality of cultural and biological diversity;

- Political instability and a lack of good governance, which are significant barriers to heritage conservation in general, and World Heritage implementation in particular;

- Greater external challenges and threats in the Pacific than in most other regions of the world, with less capacity to respond to their impacts. Examples of these external influences include climate change, financial instability, globalisation of society and economy, technological development, commercialisation, energy supply and demand, natural disasters and tourism growth;

- Climate change is of particular concern because the Pacific region is especially vulnerable to its impacts and faces many difficulties in adapting to and mitigating its effects;

- The impacts on the environment and resources (both tangible and intangible) are widespread and sometimes difficult to monitor (e.g. spread of pests and diseases), which can limit our ability to protect heritage;

- Goal and Main Actions

In the face of these challenges, our goals are to strengthen the implementation of the World Heritage Convention in the Pacific Island region and increase local, regional and global awareness, recognition and support for the conservation of the unique cultural and natural heritage of the Pacific in a way that takes into account the traditions, aspirations, opportunities and challenges of its people.

With a view to attaining these goals, and keeping in mind the “Strategic Objectives” (the Five “Cs”) adopted by the World Heritage Committee, we have identified the following “Main Actions” as a framework for implementing the Convention in our region:

- Main Actions

1. Encouraging dialogue between communities, agencies and organisations within and outside the Pacific region to identify, promote and protect the region’s outstanding cultural and natural heritage to the global community;

2. Enhancing local communities’ awareness of the benefits of preserving their cultural and natural heritage, and encouraging community participation (particularly by youth and women) in all stages of the World Heritage process.

3. Supporting successful nominations for representation on the World Heritage list, by increasing in-country capacity to identify suitable potential sites and prepare nomination dossiers that fully meet the requirements of the World Heritage Convention.

4. Increasing in-country capacity at all levels, inclusive of indigenous people to develop best practices, management plans and arrangements to ensure effective protection of Pacific heritage sites, in a way that takes into account and recognises traditional knowledge and conservation practices for land, air and sea.

5. Assisting in the development of in-country heritage expertise in the Pacific by supporting technical assistance, where requested, including the development of a network of partner institutions within the region capable of providing technical services in the area of heritage conservation in a coordinated and integrated way.

6. Building partnerships between communities, heritage agencies, regional organisations, educational institutions and non-government organisations in the region, including the promotion of multilateral, bilateral cooperation and twinning programs between World Heritage sites and countries of the Pacific and beyond.

7. Assisting communities to develop and implement environmentally sustainable economic growth through heritage-related enterprises

8. Sharing information and data bases related to heritage (through properly informed consensus), through regional strategies and communication networks that link island communities.

9. Supporting the development and implementation of effective policies and legislation for heritage by Governments in the region, including access and benefits sharing within the larger development portfolio.

10. Establishing sustainable financing arrangements to support the effective conservation of Pacific heritage and building on other available funding sources and in-kind contributions.

11. Sustaining the ongoing consultative process by bringing together the representatives of the Pacific Islands States and Territories on a regular basis.

Specific and detailed activities to give concrete implementation to the above “Main Actions” - at regional and national level – have been identified by the Pacific Delegates at the Maupiti Workshop in November 2009, and are provided in the annexed table.

| Activities at regional level | Corresponding Main Action | Relevant Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | States Parties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| Assess adequacy of existing sustainable tourism guidelines to protect and sustain natural and cultural heritage properties and if necessary develop new version adapted to Pacific context | 2,3,4,6, 7,10 |  | 2 | 1 |  |  | Advisory Bodies | World Heritage Funds | ALL | ALL | 2013 |  |
| Regional workshop to strengthen the capacities for small, low lying islands and atolls in identifying and responding to the impacts of climate change on their heritage places | 4 |  | 2 | 1 |  |  | SPC/ UNESCO Apia Office / UNESCO WHC |  |  |  |  |  |
| Develop a pilot field program to identify the impacts of coastal erosion on archaeological sites on small, low lying islands to provide data for the development of a conservation kit for communities to identify, record, collect and conserve cultural material eroding from coastal archaeological sites. (linked to Roi Mata) (linked to UNESCO SandWatch Programme) | 4 |  | 1 |  |  |  | UNESCO Apia Office |  |  |  |  |  |
| Sub-regional training workshop(s) on developing nominations and management plans. | 3, 4, 5, 9 | 2 | 2 | 1 |  |  | (World Heritage Centre / Apia Office / Australia ?) | World Heritage Fund and other | Solomon Islands; Others |  |  |  |
| Sustainable funding mechanism - Revise draft feasibility study based on consultations in Maupiti and disseminate it to state parties for review together with proposed steps forward. | 10 | 1 | 1 | 1 | 1 | 1 | UNESCO Apia Office |  |  |  | 2010 |  |
| Workshop on-site management - Managing sites with the local communities - exchange of experiences Workshop to share experiences on the integration of indigenous and other local communities in conservation strategies for heritage sites, focused on marine sites |  |  | 2 | 1 |  |  | Ministry of Heritage French Polynesia / Ministry Environment of New Caledonia | co-funding | Niue, Palau, Samoa, Rapa Nui, FSM, French Polynesia | French Polynesia | 2010-2011 |  |
| Develop regional network on local and Pacific-wide links of Marae Taputapuatea / Te Po Complex and the Marquesas archipelago through a research on sites connected, followed by a conference with neighboring countries to choose sites to be nominated and discuss how to manage them. |  | 1 | 2 |  | 2 | 2 | Ministry Heritage French Polynesia | co-funding | France, Hawaii and others |  | 2010-2011 |  |
| Polynesian Heritage Conference - WH Nominations in French Polynesia and sharing of knowledge amongst islands - tangible and intangible elements |  | 1 |  | 2 | 2 |  | Different Ministries of French Polynesia | co-funding | France, US, New Zealand, Chile and others | French Polynesia | 2010-2011 |  |
| Establish a regional dialogue to enhance links between the World Heritage Convention and the Convention for the Protection of the Intangible Cultural Heritage by establishing a project on traditional navigation and seafaring, canoe building and management of associated heritage places | 1, 4, 8 | 2 | 2 | 2 | 1 | 2 | UNESCO Apia Office |  |  |  | 2002-2015 | Ongoing |
| Develop a 'plain language' publication for public use on the World Heritage Convention for translation by PICTS into local languages. | 8 |  |  | 2 | 1 |  | Cook Islands/ UNESCO Apia Office | Australia |  |  | 2010-2011 |  |
| Develop World Heritage educational material for communities and schools including the expansion of World Heritage in Young Hands Programme throughout the region and linking it to the Pacific Education for Sustainable Development (ESD) Programme/ NB include Web 2.0 - interaction and exchange | 1,2,3,4, 5,8,9 |  |  | 2 | 1 | 2 | States Parties/ UNESCO Apia Office | World Heritage Funds | ALL | WHC and State Parties | 2010-2011 |  |
| Improving and extending communication between the UNESCO Office for the Pacific States in Apia and Pacific Island countries under non-Pacific sovereignties | 1,2,3,4,6,8 |  |  |  | 1 |  | UNESCO Apia Office | World Heritage Funds | ALL | World Heritage Centre | 2010-2015 |  |
| Develop a Pacific Heritage Research program and plan that includes the identification of research themes relevant to the region to provide background material for trans-national, serial nominations | 3 | 1 |  |  |  |  | Aotearoa/ New Zealand/ UNESCO Apia Office |  |  |  |  |  |
| Establish a Hub for Pacific Heritage to strengthen and increase communication networks, coordinate training opportunities and bring together donors and projects. The Hub would be based on the work of regionally based staff hosted by existing organizations and include a strong online component. | 1, 2, 5, 8 | 2 | 2 | 2 | 1 | 2 | UNESCO Apia Office / Australia | Australia | ALL |  | 2010-2012 |  |
| Carry out exchanges and placements using the model implemented through the African World Heritage Fund for individuals involved in the development of nominations and management of World Heritage properties | 5, 6 |  | 2 | 1 |  |  | UNESCO Apia Office |  |  |  | 2009-2015 |  |
| Establish a Pacific Heritage Academy to provide regional professional and vocational training in cultural and natural heritage management. The Academy should link to existing technical, academy and university education programs in the region. Models to be explored should include ‘virtual’ academy, locating the academy at USP with partner universities and agencies within and around the region, flexible unit and course delivery, providing both short term accredited intensive training opportunities, work placements and longer term professional education linked to undergraduate and post graduate tertiary education. The Academy will also include a regional mentoring program including exchanges and placements using the model implemented through the African World Heritage Fund for individuals involved in the development of nominations and management of World Heritage properties. Specific activities include: 1) the establishment of a steering committee with representatives from UNESCO Apia, SPC, ICOMOS Pasifika, PIMA, IUCN Oceania, SPREP (UNESCO Apia to follow up); 2) The establishment of terms of reference for a feasibility study (Steering committee). Models for the Academy. Commission a feasibility study (WHC); and 3) The review and implementation as appropriate of the recommendations of the feasibility study (steering committee). | 3, 4, 5, 8 |  | 2 | 1 | 2 |  | World Heritage Centre / UNESCO Apia Office / Australia | Australia (scoping study) | ALL |  | 2010-2012 |  |

| Actor | Activities at National Level | Corresponding "Main Actions" | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| COOK ISLANDS | Submit Tentative List 1)Complete inventory of national sites 2)National workshop (5 days) inviting ICOMOS 3)Develp OUV statements 4)Draw up List and submit | 3.4 | 1 |  |  |  |  | Ministry of Culture | World Heritage Fund |  |  | 2010 |  |
|  | Establish a World Heritage web page 1)Establish a World Heritage web page on the Ministry of Culture website 2)Simplify World Heritage Convention and translate to Cook Islands Masi | 1,2,8 |  |  |  | 1 |  | Ministry of Culture | Ministry of Culture |  |  | 2010 |  |
|  | Undertake a public awareness program on World Heritage | 2 |  |  |  | 1 | 2 |  |  |  |  |  |  |
|  | Train staff on the Focal ministry in the World Heritage process 1)Investigate the development of an exchange programme for information/knowledge including through staff exchanges in NZ (Tongario) and AUS (Kakadu) with Cook Islands heritage managers (3-6 months) 2-4 people. 2)Investigate mentoring programmes using NZ and AUS heritage managers on a 2 weeks attachment to the Cook Islands. | 3,4,5 |  |  | 1 |  |  | Ministry of Culture | New Zealand, Australia, World Heritage Fund |  |  | 2011-2013 |  |
|  | Prepare a nomination for a trans-boundary cultural site | 3,4 | 1 |  |  |  |  | Ministry of Culture |  |  |  | 2015 |  |
| FEDERATE STATES of MICRONESIA | Prepare and submit a nomination dossier (technical expertise / resources) | 3 | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Undertake a comparative analysis to establish the OUV of Nan Madol and Lelu Ruins | 3 | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Develop management plans for Nan Madol and Lelu Ruins | 4 |  | 1 |  |  |  |  |  |  |  |  |  |
|  | Workshop/training on preparing nomination and development of management plan |  | 1 | 1 | 1 | 1 | 1 | Samoa, UNESCO Apia, World Heritage Centre | World Heritage Fund |  |  | 2010 |  |

| Actor | Activities at National level | Corresponding "Main Actions" | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| FIJI | Preparing and submitting nomination for Levuka by 2010 1) Finalise the nomination dossier for Levuka 2) Review and comment on draft management plan 3)Complete legal statue framework for natural World Heritage policy | 3 | 1 |  |  |  |  | Department of Culture and Heritage/Australia, New Zealand, consultants | World Heritage Fund, Fiji Government |  |  | 2010 |  |
|  | Preparing and submitting nomination for 2nd site 1) Review Tentative List for natural and cultural site by examining sites from cultural mapping and protected area committee inventories 2) National workshop - NGO’s, Chiefs, Government 3)Provincial workshop X 3 Confederances 4)Government – sustainable develoment commitee 5)National youth workshop | 4 | 1 |  | 2 |  |  | Department of Culture and Heritage/ | World Heritage Fund, Fiji Government |  |  | 2010 |  |
|  | Seek technical advice on development of a legislative framework for National World Heritage policy | 4,9 |  |  |  |  |  |  |  |  |  | 2009 |  |
| FRENCH POLYNESIA (FRANCE) | Site management workshop – managing sites with the local communities – exchanges of experiences. | 1 2 4 5 6 7 8 |  | 2 | 1 |  | 2 | Ministry of Heritage + Environment + New Caledonia | Co-funding |  |  | 2010 – 2011 |  |
|  | Survey of the cultural and natural sites of the Marquises Islands | 1.3 | 1 |  |  | 2 | 2 | Ministry of Heritage + Environment | Co-funding |  |  | 2010 – 2011 |  |
|  | Implementing a preliminary consultation process with all the concerned peoples for the inscription on the World Heritage Listof two Polynesian heritage sites: Taputapuatea/ Te Pô, Opoa Valley and Marquises Islands | 2, 6, 7 |  |  | 2 | 2 | 1 |  |  |  |  |  |  |
|  | Polynesian heritage conference, World Heritage nomination in French Polynesia and the sharing of knowledge amongst islands, tangible and intangible elements | 2,6,8 | 1 |  |  |  | 1 | Ministry of Heritage | Co-funding |  |  | 2010 - 2011 |  |
|  | Structure regional Web on the links (local and Pacific-wide) of Marae Taputapua Tea | 1,3,8 | 1 |  |  | 2 |  | Ministry of Heritage | Co-funding |  |  | 2010 – 2011 |  |
|  | Investigate the possibility of holding a Pacific Heritage Workshop in a small island country (e.g. French Polynesia) | 1, 11 |  |  |  |  | 1 |  |  |  |  | 2010 |  |
| HAWAII (USA) | Exchange indigenous technical expertise and monitoring program design among coral reef sites in the Pacific (New Caledonia, GBRMPA, PIPA, PMNM) | 1,5,8,10 | 1 | 1 | 1 | 1 | 1 | NOAA, PIPA | Co-funding |  |  | 2012 |  |
|  | Seek partners to participate in World Sail (2012-2015) to continue voyaging traditions and connections among Pacific peoples and beyond | 1,2 |  |  |  | 1 | 1 | `Ohana Wa`a | Co-funding |  |  | 2010-2013 |  |

| Actor | Activities at National Level | Corresponding "Main Actions" | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| HAWAII (USA) | Hold in-country workshops to explore the potential advantages and disadvantages of seeking additional WH designations in Hawaii | 2,3 | 1 |  |  | 1 | 1 | National Park Service, NOAA | Co-funding |  |  | TBD |  |
|  | Facilitate networks and gatherings among indigenous experts involved in on-site cultural use planning and restoration of sites | 1,2,4,5,8 | 1 | 1 | 1 | 1 | 1 | Cultural organizations | Co-funding |  |  | Initiate in 2011 |  |
|  | Support transboundary site nomination for Taputapuatea, Te Moana Nui a Kiwa etc. | 1,6 |  | 1 |  | 1 |  |  |  |  |  | TBD |  |
|  | Assist with site restoration needs of other Pacific states (e.g. Raiatea) based on the work being done in Hawaii | 1,4,5,6 |  | 1 | 1 | 1 | 1 | Cultural organizations | Co-funding |  |  | TBD |  |
|  | Investigate the potential for a serial nomination with other Pacific Island states | 1,2,6 | 1 | 1 |  | 1 |  | National Park Service, NOAA |  |  |  | Ongoing |  |
|  | Share experiences and information between other oceanic country states between the cultural advisory group for Papahanaumokuakea (PMNM) and other like groups or organizations. | 1,2,4,5 | 1 | 1 | 1 | 1 |  | NOAA | Co-funding |  |  | Ongoing | Initiate with Marquesas in 2010 |
|  | Implement actions under the recent sister-site agreement between Papahanaumokuakea (PMNM) and Phoenix Islands (PIPA) MPAs to enhance heritage protection | 1,6,8,10 | 1 | 1 | 1 | 1 |  | NOAA | NOAA, PIPA, CI, NEAQ |  | Hawaii, Kiribati | Initiated in 2009 | Identified 2010 priorites; seeking funding |
|  | Conduct comparative research and on-site investigations of similar cultural sites (Hawaii, French Polynesia, Kiribati, Tonga, Cook Islands, Tonga, Samoa etc.) | 1,8 | 1 | 1 |  | 1 |  | University of Hawaii, NOAA, other Pacific states | Co-funding |  | TBD | Initiate in 2010 |  |
|  | Initiate parternships for climate change research and monitoring and their impacts to heritage | 1 | 1 | 1 | 1 | 1 |  | NOAA, PIPA | Co-funding |  |  | 2011 |  |
| KIRIBATI | Develop, with technical assistance, an EIA and permit system for tourism operations in Natural and Cultural heritage sites. | 3 |  | 1 |  |  |  |  | Australia |  |  |  |  |
|  | Facilitate the management of World Heritage sites through exchanges, work experience opportunities etc. | 4, 7 |  | 1 | 2 |  |  |  |  |  |  |  |  |
|  | With technical assistance identify and assess cultural values in Kiribati and the process for nominating cultural properties | 5 | 1 |  |  |  |  |  |  |  |  |  |  |

| Actor | Activities at national Level | Corresponding “Main Actions” | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| NEW CALEDONIA (FRANCE) | Share experiences and information with GBRMPA to share information on marine park management | 4, 6 |  | 1 |  |  |  | Australia & New Caledonia |  | GBR & NCR |  | 2009 | Ongoing |
|  | Develop an inventory of terrestrial natural sites in New Caledonia | 3 | 1 |  |  |  |  | GIP-CEN | Internal & NGOs |  |  | 2011 |  |
|  | Seek external support to identify a national heritage list of potential World Heritage cultural sites in New Caledonia and WF | 5 | 1 |  |  |  |  | ICOMOS France, IUCN France, New Caledonia, PR,WF | New Caledonia |  | New Caledonia, WF | 2011 | Planned |
|  | Share experiences in the integration of indigenous communities in development and implementation of management plans for World Heritage properties | 1, 8 |  | 1 |  |  | 1 | Australia & New Caledonia | SPREP, SPC, State Parties |  |  | 2009 | Ongoing |
|  | Seek financial support and technical expertise for World Heritage from State Parties with external territories in the Pacific region |  |  | 1 | 2 |  |  | ICOMOS AUS, NC, France |  | New Caledonia | New Caledonia | 2013 |  |
|  | Share experiences and information with GBRMPA with an extension to Hawaii | 4.6 | 1 | 1 | 1 |  | 1 | New Caledonia steering committee | New Caledonia & AIUS |  |  |  |  |
| NEW ZEALAND | Submit a nomination for a cultural property | 3 | 1 |  |  |  |  |  |  |  |  | Feb-10 |  |
|  | Investigate the potential for a serial nomination with Pacific Island states |  | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Assist the Cook Islands to ratify the World Heritage Convention by July 2009 | 5, 6 | 1 |  |  |  |  |  |  |  |  |  | completed |
| NIUE | Financial assistance for Tentative List preparatory ground work | 3,5 | 1 |  |  |  |  | Department of Community Affairs | World Heritage Fund, GEF, UNDP, National Budget |  |  | 2010 |  |
|  | Capacity building through a visit by four national heritage committee members to undertake an observation tour to see sites in Vanuatu and Solomon Islands | 4,6 |  |  | 1 |  |  | Department of Community Affairs | World Heritage Fund, GEF, UNDP, National Budget |  |  | 2012 |  |
|  | Legislation to cover tangible/intangible cultural and natural heritage, plus policies and guidelines | 9 | 1 | 1 |  |  |  | Department of Community Affairs | World Heritage Fund, GEF, UNDP, National Budget |  |  | 2010 |  |
|  | Local workshops to increase awareness of heritage matters | 2 |  |  |  | 1 | 1 | Department of Community Affairs | World Heritage Fund, GEF, UNDP, National Budget |  |  | 2013 |  |
|  | Youth group familiarization tour to Tongariro heritage park in New Zealand | 2, 4 |  |  |  | 1 |  | Department of Community Affairs | World Heritage Fund,,GEF, UNDP, National Budget |  |  | 2011 |  |

| Actor | Activities at national Level | Corresponding “Main Actions” | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| PALAU | Seek assistance (technical/financial) for preparation of the Rock Islands nominations by September 2009 | 3 | 1 |  |  |  |  |  |  |  |  | Sep-09 |  |
|  | Submission of the transboundary Yapese Stone Money nomination. | 3 | 1 |  |  |  |  |  |  |  |  | Feb-09 |  |
|  | Implementation of Yapese Stone Money management plan | 4 |  | 1 |  |  |  |  |  |  |  |  |  |
|  | Meetings of Palau National Commission for UNESCO with state resource management agencies and community members about World Heritage process | 6 |  |  | 1 |  | 1 |  |  |  |  |  |  |
|  | Review the tentative list and identify priority sites | 3 | 1 |  |  |  |  |  |  |  |  |  |  |
| PAPUA NEW GUINEA | Establish on-going professional skills training in heritage management & conservation planning through regional programmes | 2,4,5,6,7,8,9, 10 |  |  | 1 |  |  | PEZ, Papua New Guinea, National Commision, NCC | WH Fund, WTMA, DEWHA,DEC (PNG) |  | WTMA, Kakadu NP | 2010 – 2012 |  |
|  | Request WHC for Preparatory Assistance for nomination dossiers of sites on the Tentative List | 3.9 | 1 | 1 |  |  | 1 | PNG, National Commission, NCC | WH Fund, PNG National Commission, NCC, DEWHA, DEC |  | Papua NewG, Port Moresby | 2010 -2012 |  |
|  | Develop Institutional Arrangements for the implementation of the World Heritage Convention including establishment of PNG National World Heritage Committee for national Government endorsement and approval | 4,6,9, 10 | 1 |  |  |  |  | DEC, NCC, National Commission, UPNG, TPA, NM & AG | National stakeholders – AEC, NCC, National Commission |  | PNG, Port Moresby/DEC | 2010 |  |
|  | Resource PNG National World Heritage Committee and Secretariat for effective and better communication and implementation of heritage programmes with regional & international partners for sharing of information & data | 1,2,6,8 |  |  | 1 | 1 |  | DEC | DEWHA, DEC |  | DEC – PNG | 2010 |  |
|  | Facilitate education and awareness programmes and activities with local communities, provincial government and national government agencies and other key stakeholders for sites on the World Heritage Tentative List | 1,2,4,6,7 |  |  | 2 | 1 | 1 | DEC | WH Fund, DEWHA, DEC, NGOs, National Commission |  | Prov-Govt, communities | 2010-2015 |  |
|  | Review and update for World HeritageTentative List Sites on PNG’s tentative list | 3 | 1 |  |  |  |  |  |  |  |  |  |  |

| Actor | Activities at National Level | Corresponding “Main Actions” | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| PAPUA NEW GUINEA | Initiate Education and Awareness Activities around sites on PNG’s tentative list | 3, 5 |  |  | 1 | 2 |  |  |  |  |  |  |  |
|  | Develop a two-year mentorship project whereby a DEC Heritage Officer will, under guidance, undertake a management planning process aimed at fulfilling the World Heritage Committee’s 2008 recommendations relating to the Kuk Early Agricultural Site. | 2, 4, 5, 6, 9 |  | 1 | 1 |  |  | PNG DEC with funding & mentorship support from DEWHA | DEWHA | Kuk Early Agr. Site | DEC, PNG, Kuk, Varirata National Park | 2010-2012 | Planned |
|  | With funding assistance from National Stakeholders, DEC through Heritage Secretariat Office will facilitate for a consultant to be engaged to undertake and develop a Management Planning process aimed at fulfilling the World Heritage Management Committee’s 2008 recommendations relating to the Management Plan for Kuk World Heritage Site. |  |  | 1 |  |  |  |  |  |  |  |  |  |
|  | Development of Institutional Arrangements for the implementation of the World Heritage Convention | 5 | 1 |  |  |  |  |  |  |  |  |  |  |
| SAMOA | Conduct the comparative analysis for the 2 sites in the Tentative List to determine and confirm the OUVs for nomination process 1) Comparative analysis (natural and cultural) 2) National forum to present recommendations of OUVs of sites to all stakeholders 3) Archaeological study of sites by the national university of Samoa | 3 | 1 |  |  |  |  | Ministry of Natural Resources & Environment |  |  |  | 2010 |  |
|  | Conduct community consultations for all stakeholders (different levels – district, village, national) 1) Consultation with all village mayors, councils (chiefs – Alii me Faipule) and community groups 2) National consultation to confirm views/comments from communities etc. and to present Samoa’s nomination and the process of community | 2,3,4,6,9 |  | 2 | 2 |  | 1 |  | World Heritage Fund |  |  | 2010 |  |
|  | In-country workshop on the nomination process 1) Preparation of management plans 2) What is involved in the nomination process | 3.4 | 2 | 2 | 1 |  |  |  | World Heritage Fund/ Australia |  |  | 2010 |  |

| Actor | Activities at National Level | Corresponding “Main Actions” | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| SAMOA | Undertake a comparative analysis of natural values for the two tentative list sites to establish OUV | 3,5 | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Hold an in-country workshop on preparation of the nomination dossier | 3 | 2 |  | 1 |  |  |  |  |  |  |  |  |
|  | Hold an in-country workshop on preparation of a management plan | 4 |  | 2 | 1 |  |  |  |  |  |  |  |  |
|  | Develop WH awareness materials for schools and communities | 5 |  |  |  | 1 | 2 |  |  |  |  |  |  |
| SOLOMON ISLANDS | Completion of periodic report on the conservation state of East Rennell World Heritage site, and Retrospective Statement of Outstanding Universal Values | 1,2,3,9 | 1 | 1 | 1 |  | 1 | National commission | National and DEWHA |  |  | 2010 |  |
|  | Compile a comprehensive cultural site Data-base | 2,3,4,5,8,9 | 1 | 1 | 1 | 1 | 1 | Ministry of Culture and Tourism | National and World Heritage Fund |  |  | 2014 |  |
|  | Establish national and provincial legislation for protection of cultural and natural heritage, including policy frameworks, processes and regulations | 9 |  | 1 |  |  |  | MCT, MECM, RenBel Prov | National, WWF, POWPA, DEWHA |  |  | 2013 |  |
|  | World Heritage & Protected Area Governance strengthening at tri levels (National, Provincial, East Rennell community) |  |  | 2 | 1 |  | 2 | Nat. Com.MCT, MECM, RenBel Prov, East Rennell | DEWHA |  |  | 2013 |  |
|  | Promotion of heritage through national, provincial and local tourism & marketing plans |  |  |  |  |  | 1 | Nat. Com, MCT, MECM, RenBel Prov, East Rennell | DEWHA |  |  | 2013 |  |

| Actor | Activities at National Level | Corresponding “Main Actions” | Corresponding Strategic Objectives |  |  |  |  | Initiative taken by: | Intended funding sources | Heritage properties concerned | Venue | Proposed timeframe | Implementation Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Credibility | Conservation | Capacity-building | Communication | Community |  |  |  |  |  |  |
| TONGA | Build a strategic plan for culture and national cultural policy | 2,4,6,7,8 |  | 1 |  |  |  | Min. stry of Education and Culture, Tonga Tradition, SPC | Local and World Heritage Fund |  |  | 2011 |  |
|  | Develop management plans for heritage sites | 2,6,7,9 |  | 1 | 1 | 1 | 1 | Ministry of Education and Culture, Tonga Tradition committee, Communities |  |  |  | 2012 |  |
|  | Establish a national register of sites and surveys | 1,2,6,7 |  | 1 | 1 | 1 | 1 | Ministry of Education and Culture, Tonga Tradition |  |  |  | 2013 |  |
|  | Seek technical and financial assistance for the development of a nomination of cultural sites | 3 | 1 |  |  |  |  | Australia |  |  |  | 2010 | Ongoing |
|  | Seek technical and financial assistance for the development of a protective mechanism for the whale sanctuary | 4 |  | 1 |  |  |  |  |  |  |  |  | Ongoing |
| TUVALU | Create World Heritage awareness and educational materials for communities | 2 |  |  |  | 2 | 1 |  |  |  |  |  |  |
|  | Hold a training workshop in World Heritage for government agencies involved in cultural and natural heritage | 5 |  |  | 1 |  |  |  |  |  |  |  |  |
|  | Prepare a nomination for a site on the tentative list | 3 | 1 |  |  |  |  |  |  |  |  |  |  |
| VANUATU | Strengthen capacity of State Party to implement the World Heritage Convention | 2 |  |  | 1 |  |  |  |  |  |  |  |  |
|  | Develop a National Heritage Action Plan (technical assistance) | 4 |  | 1 |  |  |  |  |  |  |  |  |  |
|  | Heritage and tourism training for World Heritage site managers | 7 |  |  | 1 |  |  |  |  |  |  |  |  |
|  | Assistance for the development of the Roi Mata Cultural Tour to improve income generation | 7 |  | 2 |  |  | 1 |  | Australia |  |  | 2010 |  |

This Action Plan for the implementation of the World Heritage Convention in the Pacific in the period 2010-2015 was developed by Delegates of Pacific States Parties and territories at the World Heritage Regional Workshops of Cairns (Australia, October 2008) and Maupiti (French Polynesia, November 2009).

The Appeal to the World Heritage Committee from Pacific Island State Parties, also known as the “Pacific Appeal”, was developed by Pacific delegates at the February 2007 Pacific World Heritage workshop held at Waitetoko Marae (Tongariro) in New Zealand. It is annexed to Document WHC-07/31.COM/11C, accessible online from: http://whc.unesco.org/en/sessions/31COM/documents/

See reference to the five Strategic Objectives in the Operational Guidelines for the Implementation of the World Heritage Convention (version January 2008), paragraphs 25 and 26, accessible online from: http://whc.unesco.org/en/guidelines/