## Sheet1
Second Cycle of Periodic Reporting in Europe - HELSINKI ACTION PLAN
Credibility | Conservation | Capacity-Building | Communication | Communities | Priority Area(s) | Objective | # | Action | Lead partner(s) | Monitoring Indicator(s) | Regional Target for Europe before the end of the Third Cycle of Periodic Reporting | Sub-regional priorities |  |  |  | National Priority & Timeline | Comments
[12 empty] | CESEE | MED | WEST | N-B
IDENTIFICATION AND PROTECTION OF OUTSTANDING UNIVERSAL VALUE (OUV)
X |  | X |  |  | Credible and effective Tentative Lists and Nominations | Effective Updated Tentative Lists | 1 | Provide the World Heritage Centre with good practice examples for the establishment and review of Tentative Lists, to be made available on its website | States Parties World Heritage Centre Advisory Bodies | Number of good practice examples submitted to the World Heritage Centre | At least 10 good practice examples are submitted and published on the World Heritage Centre's website baseline 0 |  |  | X
X | X | [5 empty] | 2 | Establish or update national review processes for Tentative Lists to check potential OUV of sites | States Parties Advisory Bodies | Number of States Parties having established or updated their national review process | All States Parties have established or updated their national review process baseline unknown |  |  | X
X | X | [5 empty] | 3 | Update the two Gap Analyses for natural/mixed and cultural properties, depending on funding by the States Parties | Advisory Bodies | Number of updated Gap Analyses for natural/mixed and cultural properties | Two updates of Gap Analyses are completed (natural/mixed and cultural properties) baseline 0 |  |  | X
X | X | [5 empty] | 4 | Ensure funding for the update of Gap Analyses by one or more States Parties | States Parties | Amount made available for both Gap Analyses | 75 000 USD (tbc) contributed by the States Parties for the update of the two Gap Analyses baseline 0 |  |  | X
|  | X |  |  |  | Fewer failed nominations | 5 | Use existing training modules on the preparation of nominations for cultural and natural heritage and ensure funding for these training sessions by one or more States Parties | States Parties | Number of training sessions organised Number of persons trained Number of nominations prepared after attending a training session and presented to the Committee which have received a positive evaluation by the Advisory Bodies | At least four States Parties have organised training sessions on nominations for cultural and natural heritage baseline 0 At least fifty persons have been trained on nominations for cultural and natural heritage baseline 0 At least four nominations have been prepared following the aforementioned training sessions and presented to the Committee and have received a positive evaluation by the Advisory Bodies baseline 0 |  |  | X
X | X | [5 empty] | 6 | States Parties to request upstream assistance from Advisory Bodies for Tentative Lists and Nominations | States Parties | Number of nominations presented to the World Heritage Committee after receiving upstream assistance Number of sites for which Upstream advice was sought by States Parties | 20 % of nominations recommended for inscription by the Advisory Bodies had benefited from upstream assistance baseline 0 At least 10 requests for upstream assistance are submitted by the States Parties baseline 2 |  |  | X
X | X | X |  |  |  |  | 7 | Advisory Bodies to provide upstream assistance, depending on funding | Advisory Bodies | Number of States Parties' requests for upstream assistance fulfilled by the Advisory Bodies | 100 % of the upstream assistance requests funded by the States Parties are fulfilled by the Advisory Bodies baseline 100% |  |  | X
X | X | [5 empty] | 8 | Ensure that the management of sites on Tentative Lists is fully operational before nomination | States Parties | Number of sites on the Tentative Lists with fully operational management system before the submission of the nomination | 100% of sites on the Tentative Lists have a fully operational management system before the submission of the nomination baseline unknown |  |  | X
| X |  |  |  | Clear definition of OUV and its attributes | Clear definition of the OUV and its attributes as a basis for informed management decisions to ensure the effective protection of World Heritage properties | 9 | Clearly identify attributes of OUV and include them as a key component of the management plan/system | States Parties Site Managers | Number of properties with clearly defined attributes of OUV as the basis of the management system | 100% of properties have clearly defined attributes of OUV as the basis of the management system baseline unknown
| X | X |  |  |  |  | 10 | Present methodological examples for the identification of attributes of OUV with inputs from States Parties and Advisory Bodies | World Heritage Centre States Parties Advisory Bodies | Number of methodological examples on the identification of attributes published on the World Heritage Centre's website | At least three methodological examples on the identification of attributes published on the World Heritage Centre's website baseline 0
X | X |  |  |  |  | Statutory baseline information complete and accurate | 11 | Finalise all retrospective Statements of Outstanding Universal Value for adoption by the World Heritage Committee | States Parties Advisory Bodies World Heritage Centre | Number of retrospective Statements of OUV adopted by the World Heritage Committee | 368 retrospective Statements of Outstanding Universal Value for World Heritage properties in Europe adopted by the World Heritage Committee baseline 170 Statements adopted
X | X | [5 empty] | 12 | Submit all Boundary Clarifications requested in the framework of the Retrospective Inventory to the World Heritage Committee | States Parties World Heritage Centre | Number of Boundary Clarifications presented to the World Heritage Committee | 269 Boundary Clarifications for World Heritage properties in Europe presented to the World Heritage Committee baseline 208 Clarifications presented
EFFECTIVE MANAGEMENT OF WORLD HERITAGE PROPERTIES
| X |  |  | X | Effective Management Systems | Improved collaboration between the various levels of authorities | 13 | Clarify and agree upon roles and responsibilities regarding the protection and conservation of the properties between national, regional and local authorities, involving the local communities | States Parties Site Managers | Number of properties where roles and responsibilities are clearly set out in the Management Plans/Systems Number of properties where effective cooperation mechanisms between stakeholders are established | 100 % of properties have roles and responsibilities clearly set out in the Management Plans/Systems baseline unknown 100% of properties have established effective cooperation mechanisms between stakeholders baseline 35% | X |  | X
| X | [5 empty] | 14 | Improve coordination between the authorities responsible for cultural and natural heritage | States Parties | Number of States Parties that established effective cooperation mechanisms between the authorities responsible for cultural and natural heritage | 100% of States Parties have established effective cooperation mechanisms between the authorities responsible for cultural and natural heritage baseline unknown |  |  | X
| X |  |  |  |  | Effective Monitoring | 15 | Identify monitoring indicators and establish a regular monitoring system (in particular using the Periodic Reporting outcomes, the State of Conservation database, as well as the existing tools on Risk Management and Sustainable Tourism, and the resource manuals on the management of cultural and natural properties) | Site Managers | Number of properties with identified monitoring indicators Number of properties with a regular monitoring process | 100% of properties have identified monitoring indicators baseline 38% 100 % of properties have a regular monitoring process baseline 47% |  |  | X | X
| X |  |  |  |  | Prioritize management responses to highest threats identified in the Periodic Report(s) | 16 | Present and interpret Periodic Reporting results and take appropriate management actions at national and site levels | States Parties Site Managers | Number of properties where management actions have been taken on the basis of the results of the Second Cycle of Periodic Reporting | 100% of properties have used the results of the Second Cycle of Periodic Reporting to take appropriate management actions baseline 0 30% of threats identified during the Second Cycle reported as addressed during the Third Cycle of Periodic Reporting (i.e. fewer than 1850 negative factors identified as current during Third Cycle) baseline 2634 current negative factors identified during Second Cycle |  | X | X
| X | X |  |  |  | Management Planning | 17 | Tailor to the national and/or local needs the existing World Heritage Centre technical guidance documents and Manuals on managing cultural and natural heritage | States Parties Site Managers | Number of guidance documents on the management of World Heritage properties produced by the national and/or local authorities | At least 35 guidance documents on the management of World Heritage properties produced by the national and/or local authorities baseline unknown |  |  | X
| X | [5 empty] | 18 | Before the Third Cycle of Periodic Reporting, review and update Management Plans to integrate World Heritage mechanisms, or prepare them if they do not exist | States Parties Site Managers | Number of World Heritage properties with a Management Plan Number of properties for which a Management Plan has been submitted to the World Heritage Centre (new or updated) | All World Heritage properties in Europe have a Management Plan baseline 94 % The Management Plans for at least 440 properties have been submitted to the World Heritage Centre baseline 136
| X | X |  |  |  | More effective impact assessments | 19 | Training Site Managers on Heritage Impact Assessments (HIA) and/or Environmental Impact Assessments (EIA): - when to commission such assessments with regard to World Heritage properties; - how to interpret them and take appropriate actions | States Parties | Number of training activities that address Impact Assessments | At least 49 training activities carried out at national level baseline 0 | X | X | X | X
| X | X |  |  |  |  | 20 | Promote the integration of HIA into the European EIA practice via EU institutions (e.g. through the production of guidance materials with technical support from the World Heritage Centre and the Advisory Bodies) | States Parties | Steps taken towards the integration of HIA and EIA practices at EU and national levels | HIA and EIA practices are integrated on an EU and national level baseline 0 |  |  | X
| X | X |  |  | Reinforcement of interdisciplinary skillsets for Site Managers | Reinforcement of the Site Managers' technical, managerial and advocacy skills | 21 | Establish capacity-building systems for Site Managers covering, but not limited to: - management planning (including legal framework); - sustainable tourism; - managing change through an improved understanding of heritage values and other human values; - definition of OUV, and in particular of attributes, authenticity and integrity; - heritage interpretation; - disaster and/or risk management; - community engagement and resilience building | States Parties Advisory Bodies | Number of capacity-building activities Number of Site Managers trained | At least 40 capacity-building activities carried out baseline 0 At least 800 participants trained during those capacity-building activities baseline 0 | X |  | X | X
| X | X |  |  |  |  | 22 | Reinforce and/or create networks of Site Managers (national or thematic) | States Parties Site Managers | Number of active networks Number of Site Managers actively participating in a national and/or thematic network | At least 24 active networks of Site Managers baseline 6 At least 30% of Site Managers actively participate in a national and/or thematic network baseline unknown | X
| X | X |  |  |  |  | 23 | Twinning/mentoring at sub-regional, regional and/or inter-regional levels | States Parties Site Managers | Number of properties that engage in twinning/mentoring cooperation activities | At least 50% of properties engage in twinning/mentoring cooperation activities baseline unknown (45% of States Parties report engaging in twinning activities)
| X | X |  |  |  |  | 24 | Research and knowledge exchange at sub-regional and/or regional level on common threats to the OUV of properties (i.e. by type of property) | States Parties Advisory Bodies Site Managers | Number of properties engaging in sub-regional and/or regional research activities | At least 25% of properties engage in sub-regional and/or regional research activities baseline unknown |  | X
| X | X |  |  |  | Adaptation of the role of the Site Manager to a fast-changing environment | 25 | States Parties to review and update the roles and responsibilities of Site Managers ('Terms of Reference' / 'Job description') on the basis of general guidelines proposed by the World Heritage Centre and the Advisory Bodies | States Parties Advisory Bodies World Heritage Centre | Number of Site Managers' roles and responsibilities reviewed on the basis of this guidance | One guideline made available on the World Heritage Centre's website baseline 0 At least 25% of the properties have carried out a review of the roles and responsibilities of the Site Manager(s) baseline 0 | X |  | X
INCREASED AWARENESS OF THE CONVENTION
| X |  | X | X | Decision makers, especially outside the heritage sector, fully aware of WH and its benefits to society | Harnessing benefits of heritage for society through informed decision-making | 26 | Heritage practitioners and communitites advocate to increase understanding of key concepts and processes of the World Heritage Convention by the decision makers at national and regional levels, for example: - Sensitisation to World Heritage through targeted activities (e.g. 'retreats' for key actors); - Public hearings and/or consultations; - Development of national guidance materials on communication and participatory processes | States Parties Site Managers | Number of workshops and/or sensitisation activities Number of public hearings and/or consultations Number of national guidance materials on communication and participatory processes | At least 25 workshops and/or sensitisation activities organised baseline unknown At least 75 public hearings and/or consultations organised baseline unknown At least 25 guidelines on communication and participatory processes developed baseline unknown |  | X | X | X
|  | X | X | X | Community engagement and ownership of WH properties | World Heritage properties that are well cared for by the community and where the community advocates for their heritage | 27 | World Heritage professionals to: - identify and engage communities (identity mapping); - empower those communities through the formalisation of continuous participatory processes in the management systems | Site Managers | Number of properties with a Management Plan comprising a formalised framework for community participation | At least 50% of properties have a Management Plan comprising a formalised framework for community participation baseline unknown | X | X |  | X
|  |  | X | X | Awareness-raising among general public, in particular communities | Reliable and clear information on World Heritage is easily and widely available | 28 | Disseminate relevant and credible information on World Heritage, ensuring for example: - Strengthened communication with the media on World Heritage matters; - Appropriate use of the World Heritage logo; - Organisation of celebrations, Open Days and other festivities; - Use of multi-lingual communication materials, notably in English and/or French; - Use of a wide range of channels, including digital technologies, such as: (downloadable) Audio Guides, apps, dynamic links to online content, Augmented Reality, etc; - Visibility on social media platforms | Site Managers States Parties | Number of weblinks submitted to the World Heritage Centre for updated websites dedicated to information on properties Number of properties with a communication strategy and/or visibility guidelines Number of properties using digital technologies to enhance interpretation on site | At least 1 link to an updated website for each World Hertiage property in Europe submitted to the World Heritage Centre baseline unknown At least 50% of properties have a communication strategy and/or visibility guidelines baseline 21% At least 75% of properties use digital technologies to enhance interpretation on site baseline unknown |  | X |  | X
| X |  | X | X |  | Management Plans communicated to the communities | 29 | Prepare and distribute concise and understandable leaflets on Management Plans and/or Systems | Site Managers States Parties | Number of properties for which short summaries of the Management Systems have been distributed to the communities | At least 50% of properties have distributed short summaries of the Management Systems to the communities baseline unknown |  | X |  | X
|  | X | X |  | Young People ♥ World Heritage | Sustainability of educational programmes on heritage ensured | 30 | Educate and inform younger generations about heritage, notably through: - using the World Heritage in Young Hands Kit; - encouraging the organisation of World Heritage Youth Forums; - enhancing the position of heritage in national education programmes; - organising school projects and school days on World Heritage. | States Parties Site Managers | Number of States Parties using the World Heritage in Young Hands Kit Number of Youth Forums organised by the States Parties in Europe Number of properties that undertake educational programmes or initiatives with young people | 15% increase in the use of World Heritage in Young Hands Kit baseline 40% At least 4 Youth Forums organised in Europe baseline 1 20% increase in properties that undertake educational programmes or initiatives with young people baseline unknown |  | X |  | X
|  | X | X |  | World Heritage information tools widely available and used | Increased use of already existing information tools at the national and international levels | 31 | World Heritage Centre to provide information and training on existing information tools | World Heritage Centre | Number of users of the online tools in Europe (e.g. using site analytics) Number of participants in training sessions | 20% increase in the number of users of the online tools in Europe baseline tbc At least 600 persons trained in the use of the online information tools baseline 0 |  | X | X | X
X |  |  | X |  |  | World Heritage Centre's website maintained and updated with contributions from the States Parties | 32 | Maintain the World Heritage Centre's website according to the users' needs | World Heritage Centre | World Heritage Centre's website regularly maintained and improved to address the users' needs | World Heritage Centre's website regularly maintained and improved baseline unknown |  | X | X
X |  |  | X |  |  |  | 33 | Fund the updates of information tools available on the World Heritage Centre's website (e.g. the State of Conservation database, Periodic Reporting platform, presentation of good practice examples, data exchange with other inter/national databases) | States Parties | Amount contributed by the States Parties towards the update of the information tools | At least four information tools are updated through extra-budgetary funding baseline 0
|  | X | X |  |  |  | 34 | Contribute content to the World Heritage Centre's website (e.g. with good practice examples, illustrative materials, updated weblinks regarding properties, State Party reports on state of conservation, management plans) | States Parties World Heritage Centre Advisory Bodies | Number of content contributions submitted to the World Heritage Centre | At least 200 content contributions are submitted and published on the World Heritage Centre's website baseline 0 |  |  | X